## Sheet1
Anita Stacey - 1 Richmond Street Williams
Week Ending | 2025-01-24 | 2025-01-31 | 2025-02-07 | 2025-02-14 | 2025-02-21 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10 | 2025-10-17 | 2025-10-24 | 2025-10-31
Public Holidays | 2025-03-07: Labour Day - 3 Mar; 2025-04-04: Easter - 18 - 21 Apr; 2025-06-06: WA Day - June 2; 2025-09-05: Kings Bday - 29 Sept
Mean Max Temp - Deg C | 2025-01-24: 31; 2025-02-07: 30.3; 2025-03-07: 27.4; 2025-04-04: 23.1; 2025-05-02: 18.6; 2025-06-06: 15.5; 2025-07-04: 14.6; 2025-08-01: 15.4; 2025-09-05: 17.8; 2025-10-03: 21.2
Mean Rainfall - mm | 2025-01-24: 13; 2025-02-07: 17; 2025-03-07: 21.3; 2025-04-04: 29.5; 2025-05-02: 62.4; 2025-06-06: 84.4; 2025-07-04: 86.6; 2025-08-01: 67.1; 2025-09-05: 44; 2025-10-03: 31.2
Mean Rain Days per month | 2025-01-24: 2.4; 2025-02-07: 2.9; 2025-03-07: 4; 2025-04-04: 6.2; 2025-05-02: 10.9; 2025-06-06: 14.6; 2025-07-04: 15.7; 2025-08-01: 14.4; 2025-09-05: 11.2; 2025-10-03: 8.4
Council Meeting - 18 Feb | bar: 2025-02-21
Start Date - Assumed Approval (program to move accordingly) | bar: 2025-02-28
Western Power Connection - Current Status - Approved for Design | bar: 2025-01-24
Wester Power Connection - Completion - Unknown but assumed to be 8+ Months | bar: 2025-01-31 to 2025-09-26
Water to Building area (trenching & pipe lay) - (Delayed due to machinery accessability of block due to fire restrictions) | bar: 2025-04-04 to 2025-09-26
Planting of screening (shrubbery) | bar: 2025-05-30 to 2025-06-27
Shipping Container c/w shelter | bar: 2025-04-11 to 2025-07-04
Shipping Container Fencing | bar: 2025-07-11 to 2025-08-15
Transportable Assembly and Roofing | bar: 2025-03-07 to 2025-05-02
Transportable Painting | bar: 2025-04-25 to 2025-05-16
Transportable asthetic lower cladding | bar: 2025-05-09 to 2025-05-30
Front Verandah assembly, Deck oiling, Painting | bar: 2025-05-23 to 2025-06-27
Back Verandah assembly, Deck oiling, Painting | bar: 2025-06-20 to 2025-07-25
Gutters & Downpipes | bar: 2025-08-01 to 2025-08-22
Door and window trims | bar: 2025-08-29 to 2025-09-19